## Sheet1
Task Name | Duration | Start | height | Finish | height
Scope | 3 days | 2016-02-15 | 6 | 2016-02-17 | 6
Analysis/Software Requirements | 7 days | 2016-03-03 | 5 | 2016-04-02 | 5
Analysis/Software Requirements | 7 days | 2016-02-18 | 5 | 2016-04-02 | 5
Project Topic Presentation Due | 0 days | 2016-02-21 | 5 | 2016-02-21 | 5
Design, Development, & Testing in four 2-week and 1 1-week sprints | 56 days | 2016-04-01 | 4 | 2016-04-21 | 4
Design, Development, & Testing in four 2-week sprints - complete | 56 days | 2016-02-25 | 4 | 2016-04-21 | 4
Project Progress Report Due | 0 days | 2016-03-06 | 4 | 2016-03-06 | 4
Documentation | 30 days | 2016-03-23 | 3 | 2016-04-18 | 3
Documentation | 30 days | 2016-04-01 | 3 | 2016-04-18 | 3
Project Progress Report Due | 0 days | 2016-04-11 | 3 | 2016-04-11 | 3
Deployment | 5 days | 2016-04-19 | 2 | 2016-04-23 | 2
Post Implementation Review | 3 days | 2016-04-23 | 1 | 2016-04-26 | 1
Project Due | 0 days | 2016-04-30 | 1 | 2016-04-30 | 1